## Sheet1
System Generated / Filled By Mitali | [21 empty] | Filled By Mitali// should reflect to kkrishna (Operations) & Sonika (Accounts) |  |  | Filled by Krishna (Operations) |  |  | Filled By Sonika | In case of Pump in "Column E" |  |  | By Mitali | In case of Pump in "Column E" | [6 empty] | By planning | Filled by Mitali |  |  | Filled by Mitali |  |  |  |  | Should be filled by Planning Consideing the Disp. Target Dt. |  |  |  |  | Filled by Mitali |  |  | Filled by Mitali
[29 empty] | To be in Design Task |  |  |  | To be Filled by Purachase/Planning | [7 empty] | Should reflect to QC TEAM |  |  | Should reflect to planning | [9 empty] | Should reflect to Assembly & Dispatch Team
Sl. No. | SO NO. | EC No. | EC Generated Date | EC RCVD In OPERATIONS | EC sent date in Production | FILE NO. | CLIENT CODE | Client Type | Party | Naure of Supply | INDUSTRY TYPE | AGENT | Item | PO NO. | Customer PO Date | Model No. | IF PUMP (QTY) | PUMP S.NO. | ORIENTATION | LIQUID/ APPLICATION | VERSION | Payment Terms | Freight Terms | Packing Requirement | PI No. | PI Date | PI Value | Payment Status | DRG. Status | DRG SENT TO CLIENT Dt. | DRG. Approval Date | Target Dt. For Drg | BOI | Gear BOX | GB STATUS | Motor | MOTOR STATUS | PENDING PARTS / BOI Others | BOI DATE RECEIPT DATE | Target Dt. For Purchase | Required QC Documents | Target Dt. For Doc. Submission | Actual Dt. Of Doc. Submission | LD (Yes) | LD Date | DISP. TARGET DT. | Revise Disp. Target Dt | Docuemnts Required from Planning | Pump Readiness Remarks | Actual PUMP STATUS | ASSEMBLED/ PACKED QTY | Assembly date | Readiness Dt. Rcvd from Planning | Final Dt. for Packing & Dispatch | Documents Required by Assembly/Dispatch Team | Target Date for Dispatch Team | ACTUAL Material Packing Date | PLANNING STATUS | Project | Lot wise Packing slip remark | Remarks/Status/Reason of Delay | Master Reason of Delay | DISPATCH STATUS | LOT NO. | Lot Wise Disp. Dt. | Invoice Date | Order Value
(Yes/No)