## Orders
SO NO. | EC No. | EC Generated Date | Party | CLIENT CODE | Client Type | Nature of Supply | INDUSTRY TYPE | AGENT | Item | PO NO. | Customer PO Date | Model No. | IF PUMP (QTY) | PUMP S.NO. | ORIENTATION | LIQUID/ APPLICATION | VERSION | Payment Terms | Freight Terms | Packing Requirement | PI No. | PI Date | PI Value | Payment Status | DRG. Status | DRG SENT TO CLIENT Dt. | Target Dt. For Drg | BOI | Gear BOX | GB STATUS | Motor | MOTOR STATUS | BOI DATE RECEIPT DATE | Target Dt. For Purchase | Required QC Documents | Target Dt. For Doc. Submission | LD (Yes) | LD Date | DISP. TARGET DT. | Revise Disp. Target Dt | PLANNING STATUS | Project | Actual PUMP STATUS | Assembly date | DISPATCH STATUS | LOT NO. | Lot Wise Disp. Dt. | Invoice Date | Master Reason of Delay | Order Value
SO-2001 | EC-3001 | 2026-05-02 | Hindustan Zinc Ltd | HZL01 | Direct | Domestic | Sugar |  | Centrifugal Pump | PO-88001 | 2026-04-28 | HZL-200 | 2 | PS-1001, PS-1002 | Horizontal | Water | V1 | 100% Advance | Paid | Wooden Box | PI-9001 | 2026-05-05 | 1250000 | Payment Rcvd | Drg approved | 2026-05-10 | 2026-05-08 | Yes | Yes | AVAILABLE STOCK | Yes | RECEIVED | 2026-05-20 | 2026-05-18 | MTC | 2026-06-01 | No |  | 2026-06-15 |  | Completed | Zinc Plant Expansion | Packed | 2026-06-10 | Fully dispatch | LOT-1 | 2026-06-14 | 2026-06-14 |  | 1250000
SO-2002 | EC-3002 | 2026-06-01 | Tata Steel Ltd | TATA02 | Agent | Export | Non Sugar | Global Exports | Slurry Pump | PO-88002 | 2026-05-25 | TS-450 | 1 | PS-2001 | Vertical | Slurry | V2 | 50% Advance, 50% before dispatch | To Pay | Wooden Box | PI-9002 | 2026-06-03 | 860000 | Outstanding hold | Drg. Not issued |  | 2026-06-20 | Yes | No |  | Yes | PENDING |  | 2026-06-25 | IIR | 2026-06-28 | Yes | 2026-07-30 | 2026-07-05 | 2026-08-10 | In Progress | Steel Plant BOP | In plan | [5 empty] | Payment pending | 860000
SO-2003 | EC-3003 | 2026-06-20 | UltraTech Cement | UTC03 | Direct | Merchant Export | Sugar |  | Vacuum Pump | PO-88003 | 2026-06-15 | UT-90 | 3 | PS-3001, PS-3002, PS-3003 | Horizontal | Air | V1 | Advance + Balance | Paid | Loose | PI-9003 | 2026-06-22 | 415000 | Advance Rcvd & Balance payment Awaited | Drg Not Approved | 2026-06-28 | 2026-06-25 | No | No |  | Yes | RECEIVED |  | 2026-08-05 | DIMENSIONAL Report | 2026-08-10 | No |  | 2026-09-01 |  | In Progress | Cement Line 4 | Partial assembled | [6 empty] | 415000
SO-2004 | EC-3004 | 2026-07-01 | JSW Energy | JSW04 | Direct | Domestic | Non Sugar |  | Booster Pump | PO-88004 | 2026-06-27 | JS-120 | 4 | PS-4001 to PS-4004 | Vertical | Water | V3 | Net 30 | To Pay | Wooden Box | PI-9004 | 2026-07-03 | 980000 | Payment Awaited | Drg approved | 2026-07-08 | 2026-07-06 | Yes | Yes | PENDING | Yes | PENDING |  | 2026-08-20 | MTC | 2026-08-25 | No |  | 2026-09-15 |  | In Progress | Power Plant Unit 2 | Assembled | 2026-08-30 | LOT dispatch | LOT-A | 2026-09-10 | 2026-09-10 |  | 980000